## Read Me
OLD GUARD CANNABIS ADVISORS
Facility Commissioning Timeline Checklist
A phase-by-phase launch checklist for licensed cultivation, extraction, or manufacturing facilities -- the milestones that most commonly slip a launch date when they're not tracked explicitly.
How to use this
- Fill in your own Target Date per row based on your actual licensing/build timeline.
- Assign an Owner to every row -- unowned milestones are the ones that slip.
- Update Status weekly. Anything still 'Not Started' inside its own phase window is a flag.
This tool is a starting scaffold, not a substitute for a facility-specific review. Every operation's risk profile, equipment, and regulatory footprint is different.
Old Guard Cannabis Advisors ¦ oldguardcannabis.com ¦ alex@oldguardcannabis.com

## Commissioning Timeline
Phase | Milestone / Task | Target Date | Owner | Status | Notes
Pre-Construction | Finalize facility design against state canopy/room requirements
Pre-Construction | Confirm zoning & local municipal approval
Pre-Construction | Secure general liability & property insurance
Pre-Construction | Finalize capital equipment purchase orders (see Startup Budget tool)
Build-Out | HVAC / environmental controls rough-in
Build-Out | Electrical & utility service sized for full equipment load
Build-Out | Security system install (cameras, access control, alarm)
Build-Out | Seed-to-sale / track-and-trace system provisioned
Equipment Install & Commissioning | Extraction/processing equipment installed
Equipment Install & Commissioning | Equipment calibration & manufacturer commissioning sign-off
Equipment Install & Commissioning | C1D1 or equivalent hazard classification inspection (if applicable)
Systems Validation | Environmental controls validated (temp/humidity logging live)
Systems Validation | Water/utility systems tested under load
Systems Validation | Track-and-trace test transactions completed
Pre-Licensing Inspection Prep | All core SOPs finalized and version-controlled
Pre-Licensing Inspection Prep | Internal mock inspection completed against state checklist
Pre-Licensing Inspection Prep | Corrective actions from mock inspection closed out
Staffing & Training | Key production/QC roles hired
Staffing & Training | SOP-based training completed & documented for all staff
Staffing & Training | PPE and safety training completed & documented
Soft Launch | First production run under full documentation
Soft Launch | First batch QC results reviewed and signed off
Soft Launch | State inspection passed